ClaimSync Operations & Migration Runbook v2.0 · Phase 1 + Phase 2 Complete

| Project | ClaimSync — Kaaryaa GenAI Solutions |
| --- | --- |
| Owner | Anbu Chezhian |
| Channel Partner | Saleem (UAE) |
| Subscription | Kaaryaa-Azure subscription 1 |
| Subscription ID | ec12e27e-1ef9-46e9-8817-46a10b197381 |
| Resource Group | rg-claimssync-uaenorth-prod |
| Region | UAE North (uaenorth) |
| Document Date | 12 March 2026 |
| Version | v2.0 |
| Phase 1 Status | ✅ COMPLETE |
| Phase 2 Status | ✅ COMPLETE |
| Phase 3 Status | 🔜 Next — FastAPI + Blob Upload + Tenant Dashboard |

ADHICS v2 Compliant  |  Data Residency: UAE North  |  Azure RBAC Enforced

# 1. Architecture Overview

ClaimSync is a multi-tenant SaaS platform automating Abu Dhabi healthcare claims via the Shafafiya API. All data residency is UAE North per ADHICS v2.

| Phase | Scope | Image / Version | Status |
| --- | --- | --- | --- |
| Phase 0 | httpx SOAP + INI config (ClaimSync1a.py, on-prem Saleem PC) | ClaimSync1a.py | ✅ COMPLETE |
| Phase 1 | Azure UAE North infrastructure provisioning | — | ✅ COMPLETE |
| Phase 2 | Cloud engine: DBConfigProvider + KV creds + Container App Job | claimsync-engine:2.7 | ✅ COMPLETE |
| Phase 3 | Blob upload, FastAPI backend, Next.js tenant dashboard | — | 🔜 Planned |
| Phase 4 | Beta launch, VNet injection, HA upgrade, multi-tenant onboarding | — | 📋 Planned |

## 1.1 Azure Resources

| Resource | Name | Purpose |
| --- | --- | --- |
| Resource Group | rg-claimssync-uaenorth-prod | Container for all ClaimSync resources |
| PostgreSQL 16 | claimssync-db | Multi-tenant schema, sync run logs, file manifest |
| Key Vault | kv-claimssync-uae | Facility credentials, DB password (RBAC-enabled) |
| Blob Storage | stclaimssyncuae | Downloaded claim files (Phase 3 activation) |
| Container Registry | crclaimssync | Docker images for sync engine |
| Container Apps Env | cae-claimssync-uae | Runtime for sync engine jobs (static IP: 20.174.195.34) |
| Container App Job | job-claimssync-engine | Manual-trigger BAU job (Phase 2 active) |
| App Insights | ai-claimssync-uae | Monitoring, alerting, telemetry |
| Log Analytics | workspace-rgclaimssync (eb4827b3…) | Centralised log sink |
| Managed Identity | id-claimssync-engine | Keyless auth for KV + Blob + ACR |
| VNet | vnet-claimssync-uae | Private network (Private Endpoints: Phase 4) |

# 2. Phase 1 — Azure Infrastructure

✅ PHASE 1 COMPLETE — 12 March 2026

## P1-T01 — Subscription Setup

| Subscription Name | Kaaryaa-Azure subscription 1 |
| --- | --- |
| Subscription ID | ec12e27e-1ef9-46e9-8817-46a10b197381 |
| Tenant ID | 4a8ec151-3c90-4516-95c5-4c60fe32d713 |
| Account | lsanbu@gmail.com |
| State | Enabled |
| Note | Existing subscription reused. No new subscription created. |

az login

az account set --subscription "Kaaryaa-Azure subscription 1"

az account show --query "{Name:name, ID:id, TenantID:tenantId}" -o table

## P1-T02 — Resource Group

| Name | rg-claimssync-uaenorth-prod |
| --- | --- |
| Location | uaenorth |
| Provisioning State | Succeeded |
| Tags | project=ClaimSync, environment=prod, owner=Kaaryaa, cost-center=ClaimSync |

## P1-T03 — PostgreSQL 16 Flexible Server

| Server Name | claimssync-db |
| --- | --- |
| FQDN | claimssync-db.postgres.database.azure.com |
| Admin User | claimsyncadmin |
| Version | PostgreSQL 16 |
| SKU | Standard_B2ms (Burstable) |
| Storage | 32 GB |
| HA Mode | Disabled (upgrade to ZoneRedundant before Phase 4 beta) |
| Public Access | Enabled (required for Container App Consumption — no VNet injection yet) |
| Firewall Rules | allow-containerapp: 20.174.195.34 ¦ allow-azure-services: 0.0.0.0/0.0.0.0 |
| Backup Retention | 7 days |
| Location | UAE North |

Note: --high-availability flag deprecated in CLI 2.86. Use --zonal-resiliency instead.

Note: Public access was enabled during Phase 2 debug (Container App Consumption uses dynamic outbound IPs with no VNet injection). Revert to Private Endpoint only when VNet injection is implemented in Phase 4.

## P1-T04 — DB Schema

| Schema File | claimssync_schema_v2.sql |
| --- | --- |
| Tables | 11 tables: tenants, tenant_facilities, facility_subscriptions, subscription_plans, service_providers, sync_runs, sync_run_facilities, file_manifest, resellers, onboarding_requests, audit_log |
| Status | ✅ Applied to claimssync-db |
| MF2618 | tenant=KAARYAA-T1, facility=MF2618, status=active, 30-day Starter trial |
| PF2576 | Seeded but status=inactive — no KV secrets loaded, deferred to Phase 3 |

## P1-T06 — Key Vault

| Vault Name | kv-claimssync-uae |
| --- | --- |
| Vault URI | https://kv-claimssync-uae.vault.azure.net/ |
| RBAC | Azure RBAC (not legacy access policies) |
| Soft Delete | Enabled, 7-day retention |
| SKU | Standard |

| Secret Name | Purpose |
| --- | --- |
| db-admin-password | PostgreSQL claimsyncadmin password |
| facility-mf2618-userid | Shafafiya UserID for MF2618 ✅ |
| facility-mf2618-password | Shafafiya password for MF2618 ✅ |
| facility-mf2618-caller-license | Shafafiya callerLicense for MF2618 ✅ |
| facility-pf2576-* | DEFERRED — load before PF2576 Phase 3 activation |

## P1-T07 — Blob Storage

| Account Name | stclaimssyncuae |
| --- | --- |
| SKU | Standard_LRS |
| Kind | StorageV2 |
| Min TLS | TLS 1.2 |
| Public Blob | Disabled |
| Location | UAE North |
| Containers | claimssync-mf2618 ¦ claimssync-temp ¦ claimssync-pf2576 (deferred) |

## P1-T08 — Container Registry

| Registry Name | crclaimssync |
| --- | --- |
| Login Server | crclaimssync.azurecr.io |
| SKU | Basic |
| Admin | Disabled (Managed Identity pull) |

## P1-T09 — Container Apps Environment

| Environment Name | cae-claimssync-uae |
| --- | --- |
| Static Outbound IP | 20.174.195.34 |
| VNet Injection | None (Consumption plan — dynamic IPs, firewall rule added to DB) |
| Log Analytics | workspace-rgclaimssync… (eb4827b3-0541-4fc4-991d-70d733e1c092) |

## P1-T10 — App Insights

| Resource Name | ai-claimssync-uae |
| --- | --- |
| Instrumentation Key | 6d6b4002-4e78-4628-b710-1a3585901dca |
| Note | Inject as APPLICATIONINSIGHTS_CONNECTION_STRING in Phase 3 |

## P1-T11 — Managed Identity

| Identity Name | id-claimssync-engine |
| --- | --- |
| Principal ID | b4d293ed-da18-423e-a041-296fdc27b8ad |
| Client ID | 8e309ea2-175e-497e-8849-7af81a36c62a |
| Type | User-Assigned Managed Identity |
| Location | UAE North |
| Role: KV | Key Vault Secrets User — kv-claimssync-uae |
| Role: Blob | Storage Blob Data Contributor — stclaimssyncuae |
| Role: ACR | AcrPull — crclaimssync |

## P1-T12 — VNet + Private Endpoints

| VNet Name | vnet-claimssync-uae |
| --- | --- |
| Address Space | 10.0.0.0/16 |
| Subnet | snet-private-endpoints (10.0.1.0/24) |
| Status | VNet ✅ Created ¦ Private Endpoints deferred to Phase 4 |
| Note | Container App Consumption has no VNet injection support. Defer Private Endpoints until Phase 4 upgrade to Dedicated plan. |

# 3. Phase 2 — Cloud Engine Migration

✅ PHASE 2 COMPLETE — 12 March 2026 ¦ BAU RUN SUCCEEDED

Phase 2 migrates the download engine from the on-prem Windows EXE (ClaimSync1a.py) to a containerised Azure Container App Job (ClaimSync2.py). Config is sourced from PostgreSQL + Key Vault. No .ini file exists in the container — the engine is cloud-native from first boot.

## 3.1 Architecture Decision

| Engine File | ClaimSync2.py (cloud-only; ClaimSync1a.py frozen on-prem) |
| --- | --- |
| Config Source | DBConfigProvider (Azure PostgreSQL) + KeyVaultCredentialProvider |
| Invocation | python ClaimSync2.py h (BAU download — only supported mode) |
| Removed | Interactive menu, newclient/renlic/vallic, LocalINIProvider, license checks, host-lock |
| Temp Dir | /tmp/claimssync/ (all file I/O routed here — /app is read-only) |
| Blob Upload | CLAIMSSYNC_BLOB_UPLOAD=0 (Phase 3 activates) |

## 3.2 Custom Modules

| Module | Purpose |
| --- | --- |
| db_config_provider.py | DBConfigProvider(tenant_short_code, credential_provider, dsn). Queries tenants + tenant_facilities + facility_subscriptions. Returns ConfigParser-compatible dict. |
| kv_credential_provider.py | KeyVaultCredentialProvider(vault_uri). Fetches secrets by name via Managed Identity, in-process cache. |
| config_provider.py | ABC definition only (LocalINIProvider used in ClaimSync1a only, removed from ClaimSync2). |
| httpx_soap.py | soap_search_transactions(), soap_download_transaction(). Replaces curl subprocess with async-safe httpx calls. |
| blob_storage_provider.py | BlobStorageProvider — Phase 3 activation (CLAIMSSYNC_BLOB_UPLOAD=1). |

## 3.3 Container App Job

| Job Name | job-claimssync-engine |
| --- | --- |
| Resource Group | rg-claimssync-uaenorth-prod |
| Environment | cae-claimssync-uae |
| Trigger | Manual (schedule trigger: Phase 3) |
| Final Image | crclaimssync.azurecr.io/claimsync-engine:2.7 |

| Env Var | Value |
| --- | --- |
| CLAIMSSYNC_TENANT | KAARYAA-T1 |
| CLAIMSSYNC_KV_URI | https://kv-claimssync-uae.vault.azure.net/ |
| CLAIMSSYNC_TEMP_DIR | /tmp/claimssync/ |
| CLAIMSSYNC_BLOB_UPLOAD | 0 (Phase 3: set to 1) |
| AZURE_CLIENT_ID | 8e309ea2-175e-497e-8849-7af81a36c62a |
| CLAIMSSYNC_DB_DSN | secretRef: db-dsn (host=claimssync-db.postgres.database.azure.com port=5432 dbname=postgres user=claimsyncadmin sslmode=require) |

## 3.4 Image Build History & Bug Fixes

| Tag | Error | Fix Applied |
| --- | --- | --- |
| :2.1 | NameError: _os | Legacy import alias. Resolved by rebase on v8h. |
| :2.3 | shafafiaapi.ini Not Found | os.path.exists() gate never replaced. Cloud provider swap not implemented. |
| :2.4 | DB connection timeout | Implemented full Phase 2 main(): DBConfigProvider + KeyVaultCredentialProvider. DB was private-only — enabled public access + firewall rule. |
| :2.5 | NameError: systemfolder | New main() never set global. Fix: systemfolder = tempfolder. Shafafiya API: 19/19 intervals OK ✅ |
| :2.6 | PermissionError: downloadhistfileids.bat | Legacy .bat marker written to CWD (/app read-only). Fix: os.path.join(tempfolder, ...) for both write and read. |
| :2.7 | PermissionError: downloadlog-*.csv | downloadedfileslog written to CWD. Fix: os.path.join(tempfolder, ...). BAU run complete ✅ |

## 3.5 Phase 2 BAU Run Result (12 Mar 2026)

BAU RUN COMPLETE — [ClaimSync2] BAU run complete.

| Step | Result | Detail |
| --- | --- | --- |
| Config load | ✅ Success | tenant=KAARYAA-T1, DBConfigProvider + KV |
| h-claim | ✅ 19/19 OK | All 2-hr intervals, 0 failed |
| hf-claim | ✅ Pass | History forward pass |
| hff-claim | ✅ Files Found | NEURON, NEXTCARE, AAFIYA, ADNIC, NAS, THIQA |
| h-remit | ✅ 19/19 OK | All 2-hr intervals, 0 failed |
| hf-remit | ✅ Pass | History forward pass |
| hff-remit | ✅ Files Found | Remittance ZIPs located |
| Blob write | ⚠️ DISK FULL | Expected — /tmp is ephemeral. Blob upload activated in Phase 3 |
| BAU complete | ✅ DONE | [ClaimSync2] BAU run complete. |

Note: DISK FULL on blob writes is expected and by design. CLAIMSSYNC_BLOB_UPLOAD=0 is the gate. The engine correctly found real Shafafiya files and attempted to write them. Phase 3 activates blob upload — local write path is replaced by Azure Blob Storage.

## 3.6 Log Query — Container App

Use this query in Azure Log Analytics to inspect any job run:

az monitor log-analytics query \

--workspace eb4827b3-0541-4fc4-991d-70d733e1c092 \

--analytics-query "ContainerAppConsoleLogs_CL

| where TimeGenerated > datetime(2026-03-12T00:00:00Z)

| where ContainerJobName_s == 'job-claimssync-engine'

| order by time_t asc

| project time_t, Stream_s, Log_s" \

--output table

## 3.7 Trigger a Manual Job Run

az containerapp job start \

--name job-claimssync-engine \

--resource-group rg-claimssync-uaenorth-prod

## 3.8 Build & Push New Image

# In D:\KaaryaaDigital\Clients\ShafaAPI\ClaimsSync\ClaimSyncDocker

docker build -t crclaimssync.azurecr.io/claimsync-engine:2.X .

docker push crclaimssync.azurecr.io/claimsync-engine:2.X

az containerapp job update \

--name job-claimssync-engine \

--resource-group rg-claimssync-uaenorth-prod \

--image crclaimssync.azurecr.io/claimsync-engine:2.X

# 4. Key Reference Values

| Subscription ID | ec12e27e-1ef9-46e9-8817-46a10b197381 |
| --- | --- |
| Tenant ID | 4a8ec151-3c90-4516-95c5-4c60fe32d713 |
| Resource Group | rg-claimssync-uaenorth-prod |
| DB FQDN | claimssync-db.postgres.database.azure.com |
| DB Admin User | claimsyncadmin |
| DB Password | In Key Vault: db-admin-password |
| Key Vault URI | https://kv-claimssync-uae.vault.azure.net/ |
| Storage Account | stclaimssyncuae |
| Container Registry | crclaimssync.azurecr.io |
| Container App Job | job-claimssync-engine |
| Container App Env | cae-claimssync-uae |
| Static Outbound IP | 20.174.195.34 |
| Log Analytics WS | eb4827b3-0541-4fc4-991d-70d733e1c092 |
| App Insights Key | 6d6b4002-4e78-4628-b710-1a3585901dca |
| Managed Identity Principal | b4d293ed-da18-423e-a041-296fdc27b8ad |
| Managed Identity Client | 8e309ea2-175e-497e-8849-7af81a36c62a |
| Active Image | crclaimssync.azurecr.io/claimsync-engine:2.7 |
| VNet | vnet-claimssync-uae (10.0.0.0/16) |
| PE Subnet | snet-private-endpoints (10.0.1.0/24) |

# 5. Database Schema — Key Decisions

| Decision | Choice | Rationale |
| --- | --- | --- |
| Multi-SP support | Designed now, gate Phase 3 | service_provider_id on facilities from day one. is_multi_sp_enabled flag per tenant. |
| Reseller hierarchy | 3 levels, DB trigger | master → sub → individual. Trigger rejects invalid hierarchy. |
| Pricing model | Per facility/month | AED 499 Starter / 999 Pro. Catalogue in subscription_plans table. |
| Onboarding approval | Kaaryaa admin only | State machine: draft→submitted→reviewing→approved/rejected. |
| Credential storage | Key Vault only | DB stores kv_secret_prefix pointer only. Never encrypts credentials in DB. |
| Service Providers | Shafafiya live, DHA/MOH seeded | DHA and MOH rows seeded with is_live=FALSE for Phase 3. |

# 6. Phase 3 — Blob Upload + FastAPI + Dashboard

🔜 PHASE 3 — PLANNED ¦ Next Engineering Sprint

| Task | Description | Status |
| --- | --- | --- |
| P3-T01 | Activate Blob upload (CLAIMSSYNC_BLOB_UPLOAD=1) + implement BlobStorageProvider in ClaimSync2.py | 🔜 Planned |
| P3-T02 | Structured logging to PostgreSQL sync_runs + file_manifest tables after each run | 🔜 Planned |
| P3-T03 | FastAPI backend — /runs, /files, /facilities endpoints (Azure Container Apps) | 🔜 Planned |
| P3-T04 | Next.js tenant dashboard — run history, file browser, facility status | 🔜 Planned |
| P3-T05 | Scheduled trigger on Container App Job (daily / configurable cron) | 🔜 Planned |
| P3-T06 | PF2576 activation — load KV secrets, create Blob container, activate in DB | 🔜 Planned |
| P3-T07 | APPLICATIONINSIGHTS_CONNECTION_STRING wired into container env vars | 🔜 Planned |

# 7. Session Continuity Prompt

Paste the following into a new Claude session to resume exactly where we left off:

ClaimSync — Continuation Prompt (as of 12 Mar 2026 — Phase 2 Complete) Phase 0 COMPLETE: ClaimSync1a.py on Saleem's PC (C:\Users\USER\ClaimSync), frozen. Phase 1 COMPLETE: All Azure UAE North infrastructure provisioned. Phase 2 COMPLETE: ClaimSync2.py cloud engine, image :2.7, BAU run succeeded. Azure: subscription ec12e27e ¦ RG rg-claimssync-uaenorth-prod ¦ UAE North DB: claimssync-db.postgres.database.azure.com ¦ public access ON ¦ MF2618=active, PF2576=inactive KV: kv-claimssync-uae.vault.azure.net ¦ 4 secrets: db-admin + MF2618 x3 Blob: stclaimssyncuae ¦ CLAIMSSYNC_BLOB_UPLOAD=0 (Phase 3 activates) ACR: crclaimssync.azurecr.io ¦ active image: claimsync-engine:2.7 Job: job-claimssync-engine ¦ cae-claimssync-uae ¦ Manual trigger ¦ static IP 20.174.195.34 MI: id-claimssync-engine ¦ client 8e309ea2 ¦ KV+Blob+ACR roles assigned Log Analytics: eb4827b3-0541-4fc4-991d-70d733e1c092 NEXT: Phase 3 — P3-T01: Activate BlobStorageProvider (CLAIMSSYNC_BLOB_UPLOAD=1) THEN: P3-T02: DB logging (sync_runs + file_manifest) THEN: P3-T03/T04: FastAPI backend + Next.js dashboard THEN: P3-T05: Scheduled cron trigger on Container App Job FUTURE (Phase 4): VNet injection, Private Endpoints, HA upgrade, beta launch

ClaimSync  |  Runbook v2.0  |  Kaaryaa GenAI Solutions  |  March 2026  |  Phase 1 + Phase 2 Complete