ClaimsSync Azure Cloud Migration High-Level & Detailed Task Plan ¦ Dependencies Mapped ¦ Lift & Shift → Cloud-Native

| 🔵 Phase 0 Foundation | 🟢 Phase 1 Azure Infra | 🟡 Phase 2 Engine Port | 🟣 Phase 3 Dashboard | 🔴 Phase 4 Beta Launch |
| --- | --- | --- | --- | --- |

| Document | ClaimsSync Azure Migration — Task Plan v1.0 |
| --- | --- |
| Owner | Kaaryaa GenAI Solutions / Anbu |
| Approach | Lift & Shift Python engine → Azure Container App + DB-backed config + Blob Storage |
| Date | March 2026 |

# 1.  Current State — Full Architecture Map

Before defining what to change, every component of the current system is mapped precisely so nothing is missed during migration.

## 1.1  How the Current System is Triggered

There are two distinct entry points into the system:

Entry Point A — Admin / Onboarding Menu (interactive):

C:\Users\USER\Documents\MF2618\downloadTxnFilesv8b.exe

Called without arguments. Displays the admin menu:

1  Admin : New Client Onboarding    → createini()

2  Admin : Validate Licence         → decrypts validuntil, checks date

3  Admin : Renew Licence            → re-encrypts new end date into INI

9  Exit

Protected by askitsolsauthenticate() — admin password gate before any INI changes.

Entry Point B — Daily/Historical Sync (automated):

cd C:\Users\USER\Documents\MF2618

downloadTxnFilesv8b h

Argument 'h' triggers the history/sync flow. Called from:

- A Windows .bat file run manually by Saleem, OR

- Windows Task Scheduler — scheduled daily run

## 1.2  What 'h' Argument Does — The Full Sync Flow

| Step | Code Function | What It Does |
| --- | --- | --- |
| 1 | main() | Reads sys.argv[1] = 'h'. Opens log file (donwloadlog-DATETIME.log) |
| 2 | config read | Reads shafafiaapi.ini — active flag, licence dates, enchost, noofsetup |
| 3 | Licence check | Decrypts validuntil and enchost. Checks date not expired. Checks hostname matches encrypted host. |
| 4 | Setup loop | Loops over noofsetup (e.g. 2) → loads each [client-config-N]: facility, userid, password, folders |
| 5 | mainsub('h') | Determines date range: defaultsearch=y → yesterday 00:00 to now. defaultsearch=n → reads from/to from INI. |
| 6 | Interval loop | Splits date range into 2-hour windows. For each window: build SOAP XML → write request file → curl execute → save response file |
| 7 | mainsub('hf') | No-op in v8b (marker only). Legacy step kept for compatibility. |
| 8 | mainsub('hff') | Globs all response XML files → calls GetHistoryTxnFileDownload() for each |
| 9 | File download | For each FileID in response: build SOAP DownloadTransactionFile request → curl → save .xml/.zip to local claims/remittance folder |
| 10 | Archive & move | Moves downloaded files to archive folder. Handles resubmission detection and file separation. |
| 11 | Repeat | Repeats steps 5–10 for 'remit' (direction=2) after claims (direction=1). Then moves to next [client-config-N]. |

## 1.3  File System Layout (Current)

C:/Users/USER/ASKAPIV1/

├── shafafiaapi.ini              ← master config, encrypted licence

├── Temp/                        ← working temp files

├── MF2618/

│   ├── claims/                  ← downloaded claim XML files

│   ├── claims/archive/

│   ├── resubmission/

│   ├── resubmission/archive/

│   ├── remittance/

│   └── remittance/archive/

├── PF2576/

│   └── (same structure)

├── search_history_request_MF2618_claim_0.xml   ← interval request XMLs

├── search_history_response_MF2618_claim_0.xml  ← interval response XMLs

└── donwloadlog-2026-03-07-08-00-00.log

## 1.4  The Migration Target — What Replaces What

| Current Component | Azure Replacement | Migration Notes |
| --- | --- | --- |
| shafafiaapi.ini | PostgreSQL DB — tables: tenants, tenant_facilities | Full schema defined in Phase 1. INI sections map 1:1 to DB rows. |
| encryptdecrypt() for credentials | Azure Key Vault — one secret per facility credential set | Facility enters own creds on portal. Never in DB. Key Vault reference stored in DB. |
| validuntil / enchost (licence) | DB: tenant subscription tier + expiry_date + api_key | Host-lock removed. Replaced by API key auth per tenant. Expiry in DB. |
| Local folder structure | Azure Blob Storage — container per tenant, folder per facility | Path pattern: {tenant_id}/{facility_id}/claims/, /remittance/, /archive/ |
| curl subprocess (SOAP calls) | Python httpx async — native HTTPS client | curl not available/reliable in container. httpx is Azure-native Python. Same SOAP XML logic. |
| Windows Task Scheduler / .bat | Azure Container App Job — cron trigger per tenant | Daily schedule configurable per facility. Re-runnable on demand from portal. |
| Admin menu (exe interactive) | Web portal admin pages | New Client Onboarding → web form. Licence → DB subscription. Renew → portal action. |
| donwloadlog-*.log | DB table: sync_run_log + Azure Application Insights | Structured JSON logs written to DB. Full run history queryable from portal. |
| request/response XML files (temp) | In-memory (no file write for temp XML) | httpx sends SOAP body directly. Response parsed in memory. No temp files needed. |

# 2.  Master Task List — All Phases

Total estimated effort: 14–16 weeks solo developer. Each task has a unique ID, defined dependencies, and clear owner. Tasks marked [Claude] are pair-programming tasks to be done together in session.

| Phase | Task ID | Task | Depends On | Owner | Days |
| --- | --- | --- | --- | --- | --- |
| 0 | P0-T01 | Create requirements.txt with all Python deps (httpx, lxml, azure-storage-blob, azure-keyvault-secrets, azure-identity, psycopg2, arrow, cryptocode, pyotp, fastapi) | None — start here | Anbu | 0.5 |
| 0 | P0-T02 | Create Dockerfile — Python 3.12 slim, copy app, pip install, CMD entry point | P0-T01 | Anbu | 0.5 |
| 0 | P0-T03 | Refactor config loading — extract ConfigProvider abstract class with LocalINIProvider implementation (keeps existing logic working) | P0-T01 | Anbu+Claude | 1 |
| 0 | P0-T04 | Replace curl subprocess with httpx — rewrite build_and_execute_search_request() using httpx.Client SOAP POST, same XML body logic | P0-T03 | Anbu+Claude | 1.5 |
| 0 | P0-T05 | Replace curl in DownloadTransactionFile with httpx — same pattern, returns bytes directly, no temp file write | P0-T04 | Anbu+Claude | 1 |
| 0 | P0-T06 | Replace local file writes for SOAP requests with in-memory strings — eliminate search_history_request_*.xml temp files | P0-T04 | Anbu+Claude | 0.5 |
| 0 | P0-T07 | Replace local folder writes with StorageProvider abstract class — LocalFolderProvider implementation keeps existing folder logic | P0-T05 | Anbu+Claude | 1 |
| 0 | P0-T08 | Replace text log writer with structured JSON logger — same log levels (i/w/e/c), outputs JSON dict per line | P0-T03 | Anbu+Claude | 1 |
| 0 | P0-T09 | Modularise mainsub() — split into: build_intervals(), run_interval_search(), download_files(), archive_files(), run_remit() | P0-T04,P0-T07 | Anbu+Claude | 1.5 |
| 0 | P0-T10 | Write unit tests — interval windowing, XML parse, date logic, config load | P0-T09 | Anbu+Claude | 1 |
| 0 | P0-T11 | Local Docker build and test — docker build, docker run with existing INI mounted, confirm full h-flow works in container | P0-T02,P0-T09 | Anbu | 1 |
| 0 | P0-T12 | Keep admin menu functions intact but wrap behind CLI flag --admin — createini(), askitsolsauthenticate() preserved for backwards compat | P0-T03 | Anbu+Claude | 0.5 |
| 1 | P1-T01 | Create Azure subscription under Kaaryaa — enable UAE North region, set spending alerts | None (parallel to P0) | Anbu | 0.5 |
| 1 | P1-T02 | Create Azure Resource Group: rg-claimssync-uaenorth-prod | P1-T01 | Anbu | 0.5 |
| 1 | P1-T03 | Provision Azure Database for PostgreSQL Flexible Server — UAE North, Zone Redundant, claimssync-db | P1-T02 | Anbu | 0.5 |
| 1 | P1-T04 | Create DB schema — tables: tenants, tenant_facilities, sync_schedules, sync_run_log, file_manifest, sync_run_intervals (full SQL script) | P1-T03 | Anbu+Claude | 1 |
| 1 | P1-T05 | Seed existing facilities as first tenants — migrate MF2618 and PF2576 INI data into DB rows (script) | P1-T04 | Anbu+Claude | 0.5 |
| 1 | P1-T06 | Provision Azure Key Vault: kv-claimssync-uae — store MF2618 and PF2576 credentials as secrets named facility-{id}-userid and facility-{id}-pwd | P1-T02 | Anbu | 0.5 |
| 1 | P1-T07 | Provision Azure Blob Storage: st-claimssync-uae — create containers: claimssync-mf2618, claimssync-pf2576, claimssync-temp | P1-T02 | Anbu | 0.5 |
| 1 | P1-T08 | Provision Azure Container Registry: crclaimssync — for storing Docker images | P1-T02 | Anbu | 0.5 |
| 1 | P1-T09 | Provision Azure Container Apps Environment: cae-claimssync-uae | P1-T08 | Anbu | 0.5 |
| 1 | P1-T10 | Provision Azure Application Insights + Log Analytics workspace | P1-T02 | Anbu | 0.5 |
| 1 | P1-T11 | Configure Managed Identity on Container App — grant: Key Vault Secrets User, Blob Storage Contributor, DB access | P1-T09,P1-T06,P1-T07 | Anbu | 0.5 |
| 1 | P1-T12 | Configure Private Endpoints — DB and Blob Storage on VNet, Container App on same VNet | P1-T09,P1-T03,P1-T07 | Anbu | 1 |
| 1 | P1-T13 | Set up Azure Container App Job (manual trigger first, cron later) — references Docker image in ACR | P1-T09,P1-T08 | Anbu | 0.5 |
| 2 | P2-T01 | Implement DBConfigProvider — reads tenant_facilities table from PostgreSQL, replaces INI ConfigProvider | P0-T03,P1-T04 | Anbu+Claude | 1.5 |
| 2 | P2-T02 | Implement KeyVaultCredentialProvider — fetches userid/pwd from Azure Key Vault by facility secret name | P0-T03,P1-T06 | Anbu+Claude | 1 |
| 2 | P2-T03 | Implement AzureBlobStorageProvider — replaces LocalFolderProvider, writes files to Blob using azure-storage-blob SDK | P0-T07,P1-T07 | Anbu+Claude | 1.5 |
| 2 | P2-T04 | Wire DBConfigProvider + KeyVaultCredentialProvider + AzureBlobStorageProvider into main engine entry point | P2-T01,P2-T02,P2-T03 | Anbu+Claude | 1 |
| 2 | P2-T05 | Implement sync_run_log writer — on start write run record, on each interval update success/fail count, on finish write duration and status | P1-T04,P2-T04 | Anbu+Claude | 1 |
| 2 | P2-T06 | Implement file_manifest writer — for each downloaded file write FileID, FileName, blob_path, file_type, timestamp to DB | P1-T04,P2-T04 | Anbu+Claude | 1 |
| 2 | P2-T07 | Push Docker image to ACR — az acr build or docker push claimssync:v1 | P1-T08,P0-T11 | Anbu | 0.5 |
| 2 | P2-T08 | Deploy Container App Job referencing ACR image, Managed Identity, DB connection string from Key Vault | P1-T13,P2-T07,P1-T11 | Anbu | 0.5 |
| 2 | P2-T09 | End-to-end test Run 1 — trigger job manually for MF2618, verify: DB run_log written, files appear in Blob, no errors | P2-T08 | Anbu | 1 |
| 2 | P2-T10 | End-to-end test Run 2 — trigger for PF2576, verify isolation (files go to correct Blob container), run log separate | P2-T09 | Anbu | 0.5 |
| 2 | P2-T11 | Configure cron schedule in Container App Job — daily trigger per facility (default: 06:00 UAE time) | P2-T09 | Anbu | 0.5 |
| 2 | P2-T12 | Configure Azure Monitor alert — email on job failure, email on >50% interval failures in a run | P1-T10,P2-T11 | Anbu | 0.5 |
| 2 | P2-T13 | Historical backfill test — set defaultsearch=n equivalent in DB, run for 30-day window, verify all files arrive | P2-T09 | Anbu | 0.5 |
| 3 | P3-T01 | Set up FastAPI project structure — routers: /auth, /tenants, /facilities, /runs, /files, /admin | P2-T09 | Anbu+Claude | 1 |
| 3 | P3-T02 | Implement Auth — Azure AD B2C or Auth0, JWT middleware, tenant-scoped access | P3-T01 | Anbu+Claude | 2 |
| 3 | P3-T03 | Implement tenant onboarding API — POST /tenants (creates DB row + Key Vault secrets + Blob containers) | P3-T01,P1-T06,P1-T07 | Anbu+Claude | 1.5 |
| 3 | P3-T04 | Implement facility management API — CRUD for tenant_facilities, links to Key Vault for cred storage | P3-T03 | Anbu+Claude | 1 |
| 3 | P3-T05 | Implement run history API — GET /runs?facility_id=X, returns sync_run_log rows with interval breakdown | P3-T01,P2-T05 | Anbu+Claude | 1 |
| 3 | P3-T06 | Implement file browser API — GET /files?facility_id=X, returns file_manifest rows + SAS download URLs from Blob | P3-T01,P2-T06 | Anbu+Claude | 1 |
| 3 | P3-T07 | Implement manual re-run API — POST /runs/trigger (triggers Container App Job for specific facility) | P3-T01,P2-T11 | Anbu+Claude | 1 |
| 3 | P3-T08 | Build Next.js frontend — dashboard layout, login, facility list, sync status cards | P3-T02 | Anbu+Claude | 3 |
| 3 | P3-T09 | Build onboarding wizard UI — 4-field form (FacilityID, UserID, Password, ePartner), schedule picker, test connection button | P3-T08,P3-T03 | Anbu+Claude | 2 |
| 3 | P3-T10 | Build run monitor UI — live run status, last run summary, interval success/fail bar, alert history | P3-T08,P3-T05 | Anbu+Claude | 2 |
| 3 | P3-T11 | Build file browser UI — date filter, file type filter (claims/remit/resubmission), download button (SAS link) | P3-T08,P3-T06 | Anbu+Claude | 1.5 |
| 3 | P3-T12 | Build subscription management page — tier display, API key, usage stats | P3-T08 | Anbu+Claude | 1 |
| 3 | P3-T13 | Deploy FastAPI to Azure Container App (separate from sync engine) | P3-T07,P1-T09 | Anbu | 0.5 |
| 3 | P3-T14 | Deploy Next.js to Azure Static Web Apps — connect to FastAPI backend | P3-T08,P1-T01 | Anbu | 0.5 |
| 4 | P4-T01 | Migrate MF2618 — move from local client to cloud: confirm DB config, Key Vault creds, run first live cloud sync, verify against existing local files | P3-T14,P2-T09 | Anbu+Saleem | 1 |
| 4 | P4-T02 | Migrate PF2576 — same migration process as P4-T01 | P4-T01 | Anbu+Saleem | 0.5 |
| 4 | P4-T03 | Onboard first new beta facility via web portal — use onboarding wizard end-to-end, no AnyDesk | P3-T09 | Anbu | 0.5 |
| 4 | P4-T04 | Sign Saleem Channel Partner Agreement — formalise terms before approaching his clients to migrate | P4-T01 | Anbu | — |
| 4 | P4-T05 | ADHICS v2 compliance review — document data flow, credential handling, access logs, retention policy | P2-T05,P2-T06 | Anbu | 1 |
| 4 | P4-T06 | Activate subscription billing — AED 499 Starter / AED 999 Pro, payment method per tenant in DB | P3-T12 | Anbu | 1 |
| 4 | P4-T07 | Collect beta feedback — run review with pilot tenants after 2 weeks live, document issues and quick wins | P4-T03 | Anbu | 0.5 |
| 4 | P4-T08 | Tag v1.0 release in Git — freeze feature set, create changelog, document known limitations | P4-T07 | Anbu | 0.5 |

# 3.  Dependency Chain — Critical Path

The following shows the minimum critical path to get the sync engine running on Azure (end of Phase 2). Everything on this chain must complete in sequence — no skipping.

| Order | Task | Why This Must Come First |
| --- | --- | --- |
| 1 | P0-T01 | requirements.txt is the contract for every other dependency. Nothing else can be estimated or built without it. |
| 2 | P0-T03 | ConfigProvider abstraction is the interface everything else plugs into. DB, Key Vault, and local INI are all implementations of this one interface. |
| 3 | P0-T04 | httpx replaces curl before anything cloud-related is tested. curl subprocess cannot run reliably inside Azure Container Apps. |
| 4 | P0-T07 | StorageProvider abstraction must exist before AzureBlobStorageProvider can be written. Local folder must still work during dev. |
| 5 | P0-T11 | Local Docker test must pass before pushing to Azure. Catch config/import issues early, not in cloud. |
| 6 | P1-T03+T04 | PostgreSQL must be provisioned and schema created before DBConfigProvider can be coded or tested. |
| 7 | P1-T06 | Key Vault must exist before KeyVaultCredentialProvider can be coded. Secrets must be populated with real facility creds before end-to-end test. |
| 8 | P2-T01–04 | All three providers (DB, KeyVault, Blob) must be complete and wired together before any cloud test run is meaningful. |
| 9 | P2-T09 | First successful end-to-end cloud run is the gate. Nothing in Phase 3 or 4 is worth building until a real facility syncs correctly on Azure. |

Tasks that CAN run in parallel (saving calendar time):

| Track A | Track B (parallel) | Notes |
| --- | --- | --- |
| P0-T01 through P0-T11 (Python refactor) | P1-T01 through P1-T02 (Azure subscription setup) | Azure provisioning can begin while code refactor is in progress. Just needs subscription to exist. |
| P1-T03 (PostgreSQL) | P1-T06 (Key Vault) + P1-T07 (Blob) + P1-T08 (ACR) | All four Azure resources can be provisioned on the same day in any order. |
| P2-T01 (DBConfigProvider) | P2-T02 (KeyVaultProvider) + P2-T03 (BlobProvider) | All three providers can be developed simultaneously once interfaces (P0-T03, P0-T07) exist. |
| P3-T03 (Onboarding API) | P3-T08 (Next.js frontend shell) | Backend API and frontend shell can be built simultaneously, integrated at P3-T09. |

# 4.  Database Schema — INI to DB Mapping

Every field from the current shafafiaapi.ini is accounted for below. Nothing is dropped — either migrated to DB, to Key Vault, or explicitly removed with reason.

## 4.1  INI [shafaapi-main] → tenants table

| INI Field | DB Column | Table | Notes |
| --- | --- | --- | --- |
| active=y | status VARCHAR | tenants | 'active' / 'suspended' / 'trial' |
| validuntil (encrypted) | subscription_expiry DATE | tenants | Plain date in DB. No encryption needed — DB access is controlled. |
| enchost (encrypted hostname) | REMOVED | — | Host-locking eliminated. Replaced by API key auth per tenant. |
| noofsetup | COUNT of tenant_facilities rows | tenant_facilities | Dynamic — just count facility rows for this tenant. |
| systemfolder | REMOVED | — | Azure Blob replaces all local paths. No equivalent needed. |
| tempfolder | REMOVED | — | In-memory processing in cloud. No temp folder needed. |
| api_key (new) | api_key VARCHAR(64) | tenants | NEW — replaces host-lock. UUID generated on tenant creation. |

## 4.2  INI [client-config-N] → tenant_facilities table

| INI Field | DB Column | Storage | Notes |
| --- | --- | --- | --- |
| facility=MF2618 | facility_code VARCHAR | DB | Primary facility identifier |
| userid=CRH234 | kv_secret_userid VARCHAR | Key Vault ref | Stores Key Vault secret NAME, not the value. e.g. 'facility-mf2618-userid' |
| password=Crh@2024 | kv_secret_pwd VARCHAR | Key Vault ref | Never stored in DB. Key Vault secret name only. |
| direction=1 | direction SMALLINT | DB | 1=sent(claims), 2=received(remit) |
| callerLicense=MF2618 | caller_license VARCHAR | DB | Usually same as facility_code |
| ePartner= | e_partner VARCHAR nullable | DB | Optional filter |
| transactionID=2 | transaction_id SMALLINT | DB | 2=claim, 8=remit, -1=all |
| transactionStatus=2 | transaction_status SMALLINT | DB | 1=new only, 2=already downloaded |
| defaultsearch=y | default_search BOOLEAN | DB | true=yesterday-to-now. false=use from/to dates. |
| transactionFromDate | txn_from_date TIMESTAMP | DB | Only used when default_search=false |
| transactionToDate | txn_to_date TIMESTAMP | DB | Only used when default_search=false |
| minRecordCount=1 | min_record_count INT | DB | Default 1 |
| maxRecordCount=100000 | max_record_count INT | DB | Default 100000 |
| claims= / remittance= etc (paths) | REMOVED — derived from tenant_id/facility_code | Blob path | Blob path auto-constructed: {tenant_id}/{facility_code}/claims/ etc. |

## 4.3  New Tables (no INI equivalent)

| Table | Purpose & Key Columns |
| --- | --- |
| sync_schedules | cron_expr (e.g. '0 3 * * *'), timezone, enabled flag — replaces Windows Task Scheduler entry per facility |
| sync_run_log | run_id, facility_id, started_at, finished_at, status, total_intervals, intervals_ok, intervals_fail, triggered_by — replaces donwloadlog-*.log |
| file_manifest | file_id (Shafafiya FileID), run_id, facility_id, file_name, file_type (claim/remit/resubmit), blob_path, downloaded_at — replaces CSV log |

# 5.  First Coding Session — Start Here

When we open the next session to start coding, this is the exact sequence. No setup confusion, no deciding what to do first — just execute in order.

## Session 1 — P0-T01 to P0-T04 (Day 1–2)

| # | Action |
| --- | --- |
| 1 | Open downloadTxnFilesv8b.py — confirm working baseline. Run locally once to verify existing INI flow still works. |
| 2 | Create requirements.txt (P0-T01) — Claude generates, Anbu reviews and adds any missing packages from current imports. |
| 3 | Create ConfigProvider class (P0-T03) — abstract base + LocalINIProvider that wraps existing config reading. No behaviour change yet. |
| 4 | Replace curl in build_and_execute_search_request() with httpx (P0-T04) — exact same SOAP XML body, same response file save. |
| 5 | Run locally with new httpx code against PTE (staging) endpoint. Confirm response XML is identical to curl version. |
| 6 | Commit to Git. Branch: feature/phase0-foundation. Tag: v8b-cloud-ready-step1 |

Note on PTE (Staging) endpoint:

Use https://shafafiyapte.doh.gov.ae/v3/webservices.asmx for all Phase 0 and Phase 1 testing. Only switch to production endpoint when Phase 2 cloud test is confirmed stable. Confirm with Saleem whether PTE credentials exist or if we use prod credentials on PTE.

The goal of Session 1 is one thing: downloadTxnFilesv8b.py running with httpx instead of curl, producing identical results, committed to Git. Everything else in this plan builds on that one clean commit.

ClaimsSync  |  Azure Migration Task Plan v1.0  |  Kaaryaa GenAI Solutions  |  March 2026