ClaimsSync Cloud Product Release Plan UAE Health Market ¦ Multi-Tenant SaaS ¦ Azure UAE North

| Product | ClaimsSync 1.0 — Shafafiya API SaaS Platform | March 2026 |
| --- | --- | --- |
| Owner | Kaaryaa GenAI Solutions | v1.0 DRAFT |
| Target Market | UAE (Abu Dhabi, Dubai) — DHA / DOH Shafafiya Facilities | Confidential |

# 1. Executive Summary

ClaimsSync is a cloud-native SaaS platform that automates healthcare claims and remittance synchronization with the UAE Shafafiya API (DOH / DHA). Built on a proven, production-tested local automation engine (v8b), the product is now being transformed into a fully hosted, multi-tenant, subscription-based service targeting UAE health facilities, clinics, and insurance intermediaries.

The core automation already works — 2-hour interval windowing, multi-facility configs, SOAP/XML handling, archive management, and resubmission logic are all tested. The mission now is to:

- Lift-and-shift the engine to Azure UAE North (sovereign, DOH-compliant)

- Replace local INI files with a multi-tenant database layer

- Replace manual .exe execution with a scheduled, monitored cloud scheduler

- Add a web dashboard for facility onboarding, run monitoring, and log access

- Launch commercially to UAE health market under Kaaryaa GenAI Solutions

Target: First 3 paying tenants within 90 days of cloud deployment.

# 2. Strategic Context & Rationale

## 2.1  Why Now

The UAE mandatory health insurance ecosystem (Shafafiya/DOH Abu Dhabi, DHA Dubai) continues to grow. Every licensed health facility must submit and reconcile claims electronically. Most small-to-mid facilities either use manual processes or expensive legacy HIS systems that do not provide direct API sync transparency.

ClaimsSync fills a precise gap: lightweight, affordable, API-native claims sync as a managed service — no HIS lock-in, no IT infrastructure required from the facility.

## 2.2  Market Opportunity

| Segment | Size (Estimated) | ClaimsSync Fit |
| --- | --- | --- |
| Abu Dhabi Facilities (DOH) | 1,200+ licensed facilities | Direct — Shafafiya DOH |
| Dubai Facilities (DHA) | 900+ licensed facilities | Near-term — DHA API |
| Insurance TPA / Intermediaries | 30+ active TPAs | Phase 2 — bulk sync |
| KSA / Bahrain (Nphies / Malaffi) | Expanding mandates | Phase 3 — API adapter |

## 2.3  Competitive Positioning

- No known lightweight SaaS pure-play for Shafafiya sync in the market

- HIS vendors (Cerner, iHIS) are heavy, expensive, not API-focused

- ClaimsSync advantage: surgical focus, affordable, cloud-native, AI-ready

## 2.4  Kaaryaa GenAI Solutions & Network

ClaimsSync will be the first commercial product under Kaaryaa GenAI Solutions. The SaaSSandhai.AI network (Dubai office presence) and UAE-based healthcare contacts will serve as the primary early-adopter pipeline. Saleem and other co-founders can be re-engaged once a live cloud demo URL exists — a working product is the best pitch.

# 3. Architecture Transformation Plan

## 3.1  Current State (v8b — Local Desktop)

| Component | Current Implementation |
| --- | --- |
| Config | shafafiaapi.ini — local file, per-machine, plaintext credentials |
| Execution | Manual .exe / Python script trigger on Windows host |
| File Storage | C:/Users/... local folders (claims, remittance, archive) |
| Licensing | Host-locked (enchost), date-encrypted in INI |
| API Calls | curl subprocess via shell, SOAP/XML, 2-hr windowing |
| Logging | Local .log file per run, .csv file tracking |
| Multi-Tenant | Multiple [client-config-N] blocks in INI — manual setup |

## 3.2  Target State (Cloud SaaS — Azure UAE North)

| Component | Cloud-Native Target |
| --- | --- |
| Config | PostgreSQL — tenant_config table, encrypted secrets in Azure Key Vault |
| Execution | Azure Functions (timer-triggered) or Azure Container Apps — per tenant schedule |
| File Storage | Azure Blob Storage — per-tenant containers (claims/remit/archive) |
| Licensing | API-key per tenant, subscription tier in DB, JWT auth for dashboard |
| API Calls | httpx async Python client — native HTTPS, no curl subprocess |
| Logging | Azure Monitor / Application Insights + structured DB run logs |
| Multi-Tenant | Full DB-backed tenancy — web onboarding, isolated storage, per-tenant keys |

## 3.3  Cloud Stack Decision

| Layer | Selected Service | Reason |
| --- | --- | --- |
| Cloud Region | Azure UAE North (Abu Dhabi) | Data sovereignty, DOH proximity, ADHICS compliance |
| Compute | Azure Container Apps | Serverless containers, scale-to-zero, cost efficient |
| Database | Azure Database for PostgreSQL | Managed, HA, flexible server, row-level tenant isolation |
| Storage | Azure Blob Storage | Per-tenant containers, SAS tokens, lifecycle policies |
| Secrets | Azure Key Vault | Credential encryption, replacing INI encryptdecrypt |
| Dashboard | FastAPI + React (Next.js) | Python backend (consistent with existing codebase), modern UI |
| Auth | Azure AD B2C / Auth0 | Multi-tenant login, MFA for healthcare compliance |
| Monitoring | Azure Application Insights | Run tracking, failure alerts, usage dashboards |

# 4. Phased Execution Plan

| Phase | Name | Deliverable | Timeline | Status |
| --- | --- | --- | --- | --- |
| Phase 0 | Foundation Hardening | Production-ready Python module | Weeks 1–2 | In Progress |
| Phase 1 | Cloud Infrastructure | Azure resources + DB schema | Weeks 3–5 | Planned |
| Phase 2 | Engine Migration | Containerized sync engine | Weeks 6–8 | Planned |
| Phase 3 | Tenant Dashboard | Web portal + onboarding | Weeks 9–12 | Planned |
| Phase 4 | Beta Launch | 3 pilot tenants live | Weeks 13–16 | Planned |

## Phase 0 — Foundation Hardening (Weeks 1–2)

Goal: Make the existing v8b codebase cloud-ready without changing business logic.

- Refactor config loading — abstract INI reader into a ConfigProvider interface (local INI + DB-backed implementations)

- Replace curl subprocess with httpx async — eliminate shell dependency, improve error handling and timeout control

- Modularize mainsub() — break into discrete functions: fetch_intervals(), download_files(), archive_files()

- Add structured JSON logging — replace text log writes with structured log records (timestamp, tenant, level, message, metadata)

- Write unit tests for interval windowing, XML parsing, file archiving

- Create requirements.txt and Dockerfile

## Phase 1 — Cloud Infrastructure (Weeks 3–5)

Goal: Provision and validate all Azure UAE North resources.

- Create Azure subscription under Kaaryaa — enable UAE North region

- Provision: Azure Database for PostgreSQL (flexible server, Zone Redundant)

- Create DB schema: tenants, tenant_facilities, sync_schedules, sync_run_log, file_manifest

- Provision: Azure Blob Storage — container-per-facility naming convention

- Configure Azure Key Vault — store facility credentials (userid, password, callerLicense)

- Setup Azure Container Registry — push base Python Docker image

- Configure Azure Monitor + Application Insights workspace

- Setup Azure Virtual Network with private endpoints for DB and Storage

## Phase 2 — Engine Migration (Weeks 6–8)

Goal: Run the sync engine as a cloud container with DB-backed config.

- Implement DB ConfigProvider — tenant_facilities table replaces INI client-config blocks

- Implement Azure Blob StorageProvider — replace local folder writes

- Implement Key Vault CredentialProvider — replace INI password/userid fields

- Deploy as Azure Container App — trigger via Azure Container App Jobs (cron schedule per tenant)

- End-to-end test: provision test tenant in DB, run sync, verify files in Blob Storage

- Implement run logging to sync_run_log table (start, end, intervals, success/fail count)

- Implement alerting: Azure Monitor alert on job failure → email notification

## Phase 3 — Tenant Dashboard (Weeks 9–12)

Goal: Self-service web portal for facility onboarding and monitoring.

- Backend: FastAPI app — tenant CRUD, facility CRUD, run history API, file download API

- Auth: Azure AD B2C — tenant admin login, MFA, role-based (admin / viewer)

- Frontend: Next.js dashboard — facilities list, sync status, run log viewer, file browser

- Onboarding wizard: facility ID, credentials, schedule config (guided — replaces manual INI)

- Run Monitor: live status, last-run summary, interval success/fail breakdown

- File Download: browse and download claims/remittance files directly from portal

- Subscription management: trial / monthly / annual tier, API key generation

## Phase 4 — Beta Launch (Weeks 13–16)

Goal: 3 pilot tenants live on production, commercial model validated.

- Migrate existing facilities (MF2618, PF2576) as Tenant 1 — production migration

- Onboard 2 new beta facilities via SaaSSandhai.AI / UAE network

- Conduct DOH API compliance review — ensure all data handling meets ADHICS v2

- Pricing model activation: AED 499/month per facility (Starter), AED 999/month (Pro)

- Collect feedback, fix critical issues, iterate on dashboard UX

- Prepare case study from pilot tenants for sales outreach

# 5. Multi-Tenant Data Model

## 5.1  Core Tables

| Table | Key Fields | Purpose |
| --- | --- | --- |
| tenants | tenant_id, name, api_key, plan, status | Top-level organisation (clinic group, TPA, hospital) |
| tenant_facilities | facility_id, tenant_id, facility_code, direction | Maps to [client-config-N] in legacy INI. Credentials stored in Key Vault. |
| sync_schedules | schedule_id, facility_id, cron_expr, enabled | Per-facility scheduler config (replaces manual cron / task scheduler) |
| sync_run_log | run_id, facility_id, started_at, status, intervals_ok, intervals_fail | Full audit trail of every sync run — queryable for dashboard + billing |
| file_manifest | file_id, run_id, file_name, blob_path, file_type, downloaded_at | Tracks every downloaded file, replaces CSV log |

## 5.2  Tenant Isolation Strategy

- Each tenant gets a dedicated Azure Blob container: claimssync-{tenant_id}/

- Within container: {facility_id}/claims/, {facility_id}/remittance/, {facility_id}/archive/

- Credentials never stored in DB — Key Vault secret reference per facility

- Row-level security on PostgreSQL — all queries scoped to tenant_id

# 6. Go-to-Market Strategy — UAE

## 6.1  Target Buyer Profile

| Persona | Role | Pain Point ClaimsSync Solves |
| --- | --- | --- |
| Primary | Clinic / Hospital Finance Manager | Manual claim reconciliation — hours of daily work, missed files, reconciliation errors |
| Secondary | IT Manager / Healthcare IT Consultant | No lightweight API sync tool — HIS too expensive, no direct Shafafiya automation |
| Influencer | TPA / Insurance Partner | Facility filing errors cause claim delays — want facilities on automated sync |

## 6.2  Pricing Model

| Tier | Price (AED/mo) | Facilities | Includes |
| --- | --- | --- | --- |
| Trial | Free (30 days) | 1 | Full features, 1 facility, limited to 90-day history |
| Starter | AED 499 | Up to 3 | Auto-sync, dashboard, file download, email alerts |
| Pro | AED 999 | Up to 10 | Starter + API access, custom schedules, priority support |
| Enterprise | Custom | Unlimited | TPA bulk sync, white-label, SLA, dedicated support |

## 6.3  Sales Channels & Network

- SaaSSandhai.AI Dubai network — introductions to healthcare facility admins and IT consultants

- UAE HealthTech meetups / HIMSS Middle East — brand visibility

- Direct outreach: DOH facility directory — clinics, polyclinics, medical centres

- LinkedIn: target Finance Managers and Healthcare IT Consultants in Abu Dhabi / Dubai

- Referral: existing 2 facilities (MF2618, PF2576) as first case studies

- Saleem (initiator) — re-engage with live product demo and first 2 paying clients

## 6.4  90-Day Revenue Target

- Month 1: 2 pilot tenants (beta, free/discounted)

- Month 2: 3 paying tenants @ AED 499 = AED 1,497/month

- Month 3: 5 tenants @ mixed Starter/Pro = AED 3,500–5,000/month MRR

First-year ARR target: AED 60,000–120,000 (USD 16K–33K)

# 7. Risk Register & Compliance

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Shafafiya API changes / version upgrade | High | Subscribe to DOH developer notices; version-pin SOAP endpoint; adapter pattern in code |
| Data residency / ADHICS non-compliance | Critical | Deploy exclusively to Azure UAE North; document data flow for ADHICS v2 compliance review |
| Credential exposure in cloud | High | All credentials in Azure Key Vault only; never in DB or logs; Key Vault access audit logs enabled |
| Slow market adoption | Medium | Start with existing 2 facilities; leverage SaaSSandhai.AI network; free trial lowers barrier |
| Solo developer bottleneck | Medium | Modular architecture; detailed task breakdown; recruit 1 part-time frontend dev for Phase 3 |

## 7.1  Compliance Checklist

- ADHICS v2 (Abu Dhabi Healthcare Information and Cyber Security Standard) — data handling, access control, audit logs

- DOH Shafafiya API Terms of Use — per-facility credential usage, no credential sharing across tenants

- UAE PDPL (Personal Data Protection Law) — patient transaction data handling, retention policy

- ISO 27001 alignment (future) — for enterprise / TPA tier sales

# 8. Product Roadmap — Beyond v1

## 8.1  AI Layer (ClaimsSync Intelligence)

Once v1 is live and data is flowing, the AI layer transforms ClaimsSync from a sync tool into a claims intelligence platform — directly feeding Kaaryaa GenAI Solutions' positioning:

- Rejection Pattern Analysis: ML model trained on sync run data — predict rejection likelihood before submission

- Anomaly Detection: flag unusual claim volumes, duplicate submissions, outlier remittance amounts

- Smart Resubmission: AI-assisted resubmission — auto-strip attachments, suggest corrections based on rejection codes

- Natural Language Query: 'How many claims were rejected last month for MF2618?' — LLM over structured run data

## 8.2  Geographic Expansion

- Dubai Health Authority (DHA) API — adapter for DHA eClaims system (Phase 2, Month 4–6)

- KSA — Nphies (National Health Information Center) API integration

- Bahrain — Malaffi or NHRA equivalent

- Each market = new tenant namespace + API adapter + regulatory compliance layer

## 8.3  GuardRailSuite Integration

ClaimsSync generates structured audit trails, credentials flows, and API interaction patterns — ideal foundation for integrating GuardRailSuite compliance monitoring:

- AI audit trail compliance — every automated action logged and explainable

- Credential governance — Key Vault rotation policies enforced via GuardRailSuite policy engine

- ADHICS / regulatory policy as code — automated compliance checks on sync runs

# 9. Immediate Next Steps (This Week)

| # | Action | Owner | Target |
| --- | --- | --- | --- |
| 1 | Refactor v8b: replace curl with httpx, add ConfigProvider interface | Anbu (You) | Week 1 |
| 2 | Create Dockerfile + requirements.txt — test local container build | Anbu (You) | Week 1 |
| 3 | Set up Azure subscription (Kaaryaa account) — UAE North region | Anbu (You) | Week 1 |
| 4 | Design and script DB schema (tenants, facilities, run_log, file_manifest) | Anbu + Claude | Week 2 |
| 5 | Reach out to SaaSSandhai.AI Dubai contact — share product concept, seek intro to UAE facility contacts | Anbu (You) | Week 1 |
| 6 | Register Kaaryaa GenAI Solutions domain + LinkedIn page — ClaimsSync product page placeholder | Anbu (You) | Week 2 |

Remember: A working cloud URL beats any business plan. The faster you have https://app.claimssync.ai running — even with one test tenant — the faster every conversation with Saleem, SaaSSandhai.AI, or any facility changes.

ClaimsSync | Kaaryaa GenAI Solutions | Confidential | March 2026